## Sheet1
Vulnerability Name | Risk Description | Threat Source | Existing Controls | Likelihood of Occurrence | Impact Severity | Risk Level | Potential Best Practice Control | Comments | Organizational Owner
Cloud provider fails to periodically conduct a risk assessment including penetration testing (including web application security) | Information maintained by the cloud provider is compromised | Adverserial, accidental, structural, environmental, etc. | None | High | High | High | Obtain assurances that cloud provider conducts periodic risk assessments, including information about who conducts risk assessment, how often, and whether such assessments include penetration testing.
Cloud provider has inadequate administrative, physical, and technical safeguards | Information maintained by the cloud provider is compromised | Adverserial, accidental, structural, environmental, etc. | None | High | High | High | Obtain documentation that cloud provider has a comprehensive security program that adheres to a recognized framework (e.g., ISO) and is periodically reviewed by a third party.
Unauthorized access during transmission to cloud provider | Information is intercepted and exploited by an unauthorized third party during transmission to the cloud provider | Adversarial outsider (e.g., hacker) | Information sent to cloud provider is encrypted in transit | Low | High | Low | No additional control necessary
Weak password protections for cloud services | Unauthorized person is able to obtain access to information by guessing a password | Adversarial insider or outsider | Vendor default password and no administrative password policy | Moderate | High | Moderate | Turn on vendor feature requiring strong passwords and implement policy prohibiting weak password practices
Unlimited password attempts for cloud services | Unauthorized person uses automated attack to obtain passwords | Adversarial outsider (e.g., hacker) | Vendor default does not limit password attempts | Moderate | High | Moderate | Turn on vendor feature limiting failed login attempts
Social engineering attempt to obtain password to cloud services | Unauthorized person obtains password by posing as insider (e.g., IT department) | Adversarial outsider (e.g., hacker) | None | Moderate | High | Moderate | Institute policy and provide training that users may not share passwords with others, including IT department
Password to cloud services is written down and available to unauthorized persons | Unauthorized person obtains copy of written password to cloud services | Adversarial insider or outsider | None | Moderate | High | Moderate | Institute policy and provide training that users may not write down passwords and leave unattended
Download of cloud information | Authorized user downloads local copy of information from cloud onto unsecure device, which is lost or stolen | Users | None | High | High | High | Determine appropriate download policy (e.g. information may only be downloaded in limited circumstances and only to properly secured devices)
Corruption during transit | Information is partial or incorrect (e.g. due to packet loss), resulting in patient safety concerns due to incomplete medical information | Accidental | Software application checks integrity of transmitted data | Very Low | High | Low | No additional control necessary
Service outage at cloud provider | Lack of access to information, potentially including electronic health records and billing information | Accidental or environmental | None | Moderate | High | Moderate | Evaluate business continuity and disaster recovery options (e.g. from cloud provider or through on-premise recovery) and implement and test appropriate solution.
Service outage at local internet service provider | Lack of access to information, potentially including electronic health records and billing information | Accidental or environmental | None | High | High | High | Maintain reasonably current local backup of critical information and test ability to recover information
Loss of local power | Lack of access to information, potentially including electronic health records and billing information | Environmental | None | High | High | High | Maintain backup generator for powering critical IT systems and use local backup
Public-facing neglected assets with open ports | Sensitive data exposure through open ports on public-facing assets. | Adversarial outsider (e.g., hacker) | Regular audits and monitoring of open ports. | High | High | High | Continuous monitoring and automated alerts for unauthorized access. | Ensure all public-facing assets are included in the audits. | IT Security Team
Vulnerabilities in code repositories | Severe vulnerabilities in code repositories could be exploited by adversaries. | Adversarial outsider (e.g., hacker) | Code repository scanning and vulnerability management. | High | High | High | Regular vulnerability assessments and patch management. | Focus on high-priority vulnerabilities first. | Development Team
Root user or account owner without MFA | Lack of MFA for root user or account owner increases risk of unauthorized access. | Adversarial insider or outsider | Implementation of MFA for all critical accounts. | Moderate | High | Moderate | Mandatory MFA implementation for all users. | Regularly review MFA enforcement. | IT Security Team
Unclear responsibility boundaries in the shared responsibility model | Shared responsibility model may lead to unclear boundaries and unaddressed risks. | Organizational misalignment | Documented shared responsibility model with defined boundaries. | Moderate | Moderate | Moderate | Establish clear communication channels and regular reviews. | Conduct joint risk assessments with the cloud provider. | Cloud Strategy Team
Misaligned incentives or limited liability in SLAs | SLAs may result in misaligned incentives, limited liability, or unmet service expectations. | Cloud provider and organizational misalignment | Comprehensive SLA with clearly defined terms and regular reviews. | Low | Moderate | Low | Negotiate clear SLAs with penalties for non-compliance. | Periodically review SLAs to ensure they remain aligned with business goals. | Legal & Procurement Team
Data Breaches | Unauthorized access to sensitive data stored in the cloud, leading to data leaks. | Adversarial outsiders (e.g., hackers), insider threats | Encryption, access control policies, regular security audits. | High | Very High | High | Implement advanced threat detection, continuous monitoring, and incident response plans. | Ensure continuous updates to security controls as threats evolve. | IT Security Team
Insider Threats | Malicious or unintentional actions by insiders that compromise cloud security. | Malicious insiders, employees | Employee training, access restrictions, monitoring insider activities. | Moderate | High | High | Enhance insider threat programs, improve access management, and establish stringent controls. | Regularly review and update access privileges and monitoring protocols. | Human Resources & IT Security Team
Compliance Violations | Non-compliance with regulatory requirements for data storage and processing. | Regulatory bodies, internal compliance failures | Regular audits, compliance checks, adherence to data protection regulations. | Moderate | High | Moderate | Maintain up-to-date knowledge of regulations, employ automated compliance tools, and conduct regular assessments. | Establish a dedicated compliance team to oversee regulatory adherence. | Compliance Team
Inadequate Cloud Configuration | Misconfigurations in cloud settings could expose the organization to attacks. | Human error, lack of expertise | Configuration management tools, regular audits, automated scanning for misconfigurations. | High | High | High | Adopt best practices for cloud configuration management, enforce automated compliance checks. | Provide ongoing training to staff on cloud configuration best practices. | Cloud Operations Team
Lack of Cloud Visibility | Difficulty in monitoring and auditing cloud environments, leading to blind spots. | Lack of proper monitoring tools, mismanagement | Use of cloud management and monitoring tools, logging, and alerting systems. | Moderate | Moderate | Moderate | Enhance cloud visibility through integrated monitoring and auditing tools. | Regularly review and update monitoring tools to cover all cloud environments. | Cloud Operations Team
Vendor Lock-In | Difficulty in migrating away from a specific cloud provider due to proprietary technologies or complex contracts. | Cloud provider's proprietary technologies, complex contracts | Strategic planning, negotiation of flexible contracts, use of multi-cloud strategies. | Low | Moderate | Low | Ensure contract flexibility, develop exit strategies, and consider hybrid or multi-cloud environments. | Consider alternative providers and avoid vendor lock-in through diversified strategies. | Legal & Cloud Strategy Team
Denial of Service (DoS) Attacks | Overloading cloud services to disrupt operations. | Adversarial outsiders (e.g., hackers), script kiddies | DDoS protection services, traffic monitoring, and filtering. | Moderate | High | Moderate | Deploy DDoS mitigation solutions, enhance network resilience, and conduct regular tests. | Regularly review DDoS protection measures and conduct penetration testing. | IT Security Team
Data Loss | Accidental deletion or loss of data without proper backup and recovery processes. | Human error, technical failures | Regular backups, disaster recovery plans, use of cloud-native backup solutions. | Moderate | High | High | Implement automated backup solutions, regularly test disaster recovery plans, and educate staff on data handling. | Ensure regular data backup processes are automated and thoroughly tested. | Cloud Operations & IT Security Team